## Task Tracker
ID | Workstream | Task | Owner | Start | Due | Status | Priority | Days | Overdue?
T-01 | Discovery | Confirm stakeholders and objectives | PM | 2026-11-02 | 2026-11-05 | Done | Medium | 3
T-02 | Discovery | Document current inventory process | Business Analyst | 2026-11-03 | 2026-11-07 | Done | Medium | 4
T-03 | Discovery | Approve scope and success criteria | Sponsor | 2026-11-07 | 2026-11-09 | Done | High | 2
T-04 | Requirements | Interview store and warehouse users | PM | 2026-11-09 | 2026-11-13 | Done | Medium | 4
T-05 | Requirements | Define inventory data fields | Analyst | 2026-11-11 | 2026-11-16 | Done | High | 5
T-06 | Requirements | Review e-commerce integration needs | IT Lead | 2026-11-14 | 2026-11-19 | In Progress | High | 5
T-07 | Requirements | Sign off requirements | Sponsor | 2026-11-19 | 2026-11-22 | Not Started | High | 3
T-08 | Configuration | Configure inventory categories | IT Lead | 2026-11-21 | 2026-11-28 | In Progress | Medium | 7
T-09 | Configuration | Set up stock thresholds and alerts | IT Lead | 2026-11-25 | 2026-12-01 | Not Started | Medium | 6
T-10 | Configuration | Create sample data migration map | Analyst | 2026-11-27 | 2026-12-03 | Not Started | High | 6
T-11 | Testing | Draft user acceptance test plan | QA Lead | 2026-12-01 | 2026-12-05 | Not Started | High | 4
T-12 | Testing | Test receiving and stock adjustment | QA Lead | 2026-12-05 | 2026-12-11 | Not Started | High | 6
T-13 | Testing | Test order and inventory sync | QA Lead | 2026-12-09 | 2026-12-15 | Not Started | High | 6
T-14 | Testing | Resolve priority defects | IT Lead | 2026-12-14 | 2026-12-20 | Not Started | High | 6
T-15 | Rollout | Prepare staff training guide | PM | 2026-12-15 | 2026-12-21 | Not Started | Medium | 6
T-16 | Rollout | Run pilot in one store | Store Manager | 2026-12-21 | 2026-12-26 | Not Started | High | 5
T-17 | Rollout | Go/no-go readiness review | Sponsor | 2026-12-26 | 2026-12-28 | Not Started | High | 2
T-18 | Rollout | Roll out and monitor stabilization | PM | 2026-12-28 | 2027-01-04 | Not Started | High | 7
Formulas:
Overdue? = IF(AND([Status]<>"Done",[Due]<TODAY()),"Overdue","")

## Risk Register
ID | Risk | Likelihood (1-5) | Impact (1-5) | Severity | Owner | Mitigation / Response | Status | Score
R-01 | Inventory data inconsistent across locations | 4 | 4 | High | Analyst | Validate SKU mapping; reconcile pilot sample | Open | 16
R-02 | E-commerce inventory sync delays | 3 | 5 | High | IT Lead | Test integration early; define rollback | Open | 15
R-03 | Store staff adoption lower than expected | 3 | 3 | Medium | Store Manager | Training sessions and quick reference guide | Open | 9
R-04 | Scope changes threaten schedule | 3 | 4 | High | PM | Formal change log and sponsor approval | Open | 12
R-05 | Cutover causes temporary stock inaccuracies | 2 | 5 | High | IT Lead | Backup export; staged pilot and rollback | Mitigating | 10
R-06 | Key stakeholder unavailable for signoff | 2 | 3 | Medium | PM | Book review sessions in advance | Closed | 6

## Milestones
Milestone | Target Date | Owner | Status | Acceptance Criteria
Charter approved | 2026-11-09 | Sponsor | Done | Sponsor approves scope and objectives
Requirements signed off | 2026-11-22 | Sponsor | Not Started | Requirements and data fields approved
Configuration complete | 2026-12-03 | IT Lead | Not Started | Core inventory flows configured
User testing complete | 2026-12-20 | QA Lead | Not Started | Critical test cases pass
Pilot approved | 2026-12-28 | Sponsor | Not Started | Go/no-go decision recorded
Rollout complete | 2027-01-04 | PM | Not Started | Staff trained; monitoring established

## Dashboard
RETAIL INVENTORY SYSTEM ROLLOUT ¦ PROJECT CONTROL CENTER
KPI | Value | Status | Count
Total Tasks | 18 | Done | 5
Completed Tasks | 5 | In Progress | 2
Completion Rate | 27.78% | Not Started | 11
Blocked Tasks | 0 | Blocked | 0
Open Risks | 5
Workstream | Tasks
Discovery | 3
Requirements | 4
Configuration | 3
Testing | 4
Rollout | 4
SIMULATED CASE STUDY — edit task statuses and risk records to update metrics.